## Re. Ver (hidden)
OK |  | Doing |  | Date line | Emergency important
No. | Date | Ver. | Conten |  |  | Note
1 | 2017-11-28 | 1 | Start make file history make program
2 | 2017-11-29 | 1.01 | Revise step list
3
4
5
6
7
8

## JOB list
No. | Name | PIC | Detail | Finish | Delay | Result | Time (h) | Experience | Note
1 | Build up base of program | DAT | Camera connect | 2018-01-22 |  | ok
2 |  | DAT | Algorithm & Opencv | 2018-01-24 | Improving | ok |  | Shape tract, pattern matching, | 1,2,3,4….100
2 |  | DAT | Capture | 2018-01-25 |  | ok |  | Video processing
3 |  | DAT | Video | 2018-01-26 |  | ok
3 | Interface | DAT | Show image | 2018-01-26 |  | ok
4 |  | DAT | Show to frame | 2018-01-29 |  | ok
4 |  | DAT | control box,button,textbox | 2018-01-31 |  | ok
|  | DAT | Menu | 2018-01-31 | Investigating
|  | DAT | Show Area check | 2018-01-31 |  | ok
|  | DAT | Scan area by click mouse | 2018-01-31 |  | ok
5 | Processing data (text file) | DAT | Save Image | 2018-02-01 |  | ok
5 |  | DAT | Make text file | 2018-02-02 |  | ok
6 |  | DAT | Load data from text file | 2018-02-03 |  | ok
6 |  | DAT | Save data to text file | 2018-02-10 |  | ok
7 | Connect with external equipment | DAT | Receive from PLC (receive takepic signal) | 2018-02-24 |  | ok
7 |  | DAT | Send result to PLC (OK/NG) | 2018-02-28 |  | ok
8 | Test | DAT | Rubber | 2018-03-16 |  | ok
8 |  | DAT | PCB | 2018-03-30
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## TCPIP (hidden)
No. | Step | Conten | Note
1 | Add sver thread | huy add sever thread at : stepcontrothread.cpp line :2792-2820. add 3 thread StaticThread_Server(LPVOID pParam); Thread_Server() StartServer() | huygo 23.nov.2017
2 | chat lan | Trung add client to connect and take picture | Chatlan
3 | Take data and convert to string | using 3 class to take data, convert data
4 | Take data converted OK to Stepcontrothread.cpp
5 | END | Can't contro sever thread ==> change methrod
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28

## Q & A (hidden)
Q & A for Visual Inspection Team
No. | Question | Request by | Answer | Reply by | Note | Check by
1 | How to make and expand E63, E64 ? | Hien | 1. Fist ( must follow 7 job list of AED) .This is request by user so you don't need do step 1 ; Only receiver request by user. All other process normal. 2. This JIG using for new printer models , you should known to process after you making JIG OK, ready for running . Setup line , confirm checker, MT1, MT2, MP. Some process you must do more than one times. 3. Canoner call this MT season , and many event changing point during it; you must update everyday. and analyze data to keep out JIG run OK. | Trung
2 | How to contact? | Hien | 1. Of cause we don't and won't working alone. 2. You should known some things about structure or ( organize ) of CVN also TL- factory. Which department and their mission ? 3. Some Dep't you must confirm are : Assy (make printer-user Ms. Hong ));PM-Assy ( set up JIG Mr. Viet ( 1649); MTS (new model for assy Ms. Hoan (1412));PQA ; PED ( co-operation to make checker Ms. Linh); PE1( giver step list don't clear ); ..... | Trung
3 | Your programing skill not enough. | Hien | 1. What did you mean? 2. All most frame and function of program we already finish ( all most same E55 ); pls understand more about image processing. And MFC code ; it very easy if you have enough passion with technology. And very difficult if you only love money. | Trung
4 | How to new model run mass production (MT)? | Hien | 1. other dep't prepare 5 M OK -> your JIG OK -> you must confirm with other dep't ability of your JIG ( also all JIG in line ) -> make report to Japan -> JP decided Start -> MT start -> you follow . 2. If have trouble in MT : 1> stop line keep phenomenon . And report to all dep't related. 2> Take picture and data . 3> repair and keep line run. 4> Investigate root cause, make report. -meeting . 5> Give countermeasure and patement action; | Trung
5 | Need oder or design more? | Hien | 1. Of cause you must design special , or der part follow ( in cluse 7 job ) now you can do it now because we have one printer of D51 ( appearance same E63). 2. You report to leader to arrange mechanical member design JIG. 3. E63,64 JIG part list order is very esay we will do ing together | Trung
6 | When we start ? Who will support you? | Hien | 1. Now we have plan to new model . You must start make schedule and arrange your time to make specical. 2. I ( Trung ) will support you all time , and some time Mr. Sy will training you Debug Skill. Mr Huy support you programing. | Trung
7 | How about plan? Times? | Hien | I am not you ! You must using you skill and all information, all thing we infom to you to make schedule. -> I follow you schedule don't reverse. Other member in team is checker not do all thing replace you. | Trung
8 | ?????????????? | Hien | OK I am main supporter of you . Try you best! | Trung
9 | What is different of MT1 and MT2 ? | Hien | MT2 using to confirm kaizen point of MT 1 , prepair to MP. Condition of MP same MT2 not MT1.but you hab better make JIG run satble from MT1. | Trung
10 | What happen will be ? How to solve? | Hien | 1. MT problem --> check Q4? 2. Bug program when coding -> always back up you program and take note history. Remember ! You are only person in the Word know what are you doing? 3. Think before you change every thing will make you better. 4. Report every day help you easy solve problem with you leader. 5. Take picture and keep evidence for each action of you. ( if you haven't finish please report the trurt ). | Trung
11 | Are you self-confident ? And what are you opinion for this project? | Trung |  |  | Remember ! You think you can or you can't you always true.

## JOB list AED (hidden)
AUTOMATION ENGINEERING WORK PROCEDURE (STEP LIST)
Item: |  |  | Start Date:
PROCESS |  | TO DO JOB LIST | REF. TIME | REQUIRED DOCUMENTS | PLAN | ACTUAL | ACCEPTANCE
[7 empty] | LEADER | AMG | MGR up
01 | PRODUCTION PROCESS STUDY | 1.1. View current layout :make actual image (previous and next process) | 2 days | 1. Layout sheet
|  | 1.2. Detail operation: making timing chart; katsujin calculate targe cost follow efficiency 2 year | 1 day | 2. Timming chart with calculation sheet
|  | 1.3. All document related: product dwg; work STD; PS | 1 day | 3. Dwg; PS
|  | 1.4. Summarize data of current work (production/NG rate: … | 2 days | 4. NG record
|  | 1.5. Kaizen process | -
|  | 1.6. Making report | 2 days | 5. Report document
|  | 1.7. Get request sheet from user, then get approval, Issue draft, schedule | 3 days | 6. Approval sheet and schedule
2 weeks
02 | BUILD UP SPECIFICATION | 2.1. Making idea for Kakouten | 2 days | 7. Drawing of idea
|  | 2.2. Gathering all technology and equipment need | 1 week | 8. Manual and data sheet
|  | 2.3. Test kata for each work by making mock-up | 3 weeks | 9. Data of testing
|  | 2.4. Select final idea of Kata | 2 days | 10. Drawing of idea with approval
|  | 2.5. Making image of Mecha, final layout follow final idea, mc timming chart, confirm with user. | 1 week | 11. Image of machine, timming chart
|  | 2.6. Issue final specification sheet, then get approval | 3 days | 12. Specification sheet
|  | 2.7. Meeting with maker if order all to out side to get quotation | - | 13. Mtg minute.
|  | 2.8. Estimate 1 step of cost then calculate efficiency | 2 days | 14. Calculate sheet
|  | 2.9. Explain, to TOP management (approval for idea) | 2 days | 15. Report document
|  | 2.10. Review schedule, making more detail | 1 day | 16. Detail schedule
7 weeks
03 | MAKING DWG | 3.1. Making 3D with Kata and Mecha | 3 weeks | 17. Data sheet of equipment
|  | 3.2. Electrical layout, select device | - | -
|  | 3.3. Review 3D with all related dep't and revise (User/MTP/ISH/QA/PE…) | 1 week | 18. Review record
|  | 3.4. Issue ,2D machanical dwg | 3 weeks | -
|  | 3.5. 2D Review (with MTP member) | -
|  | 3.6. Issue electrical dwg | - | -
|  | 3.7. Ask maker to estimate, quotation (for all part) | 1 week | 19. All quotation
|  | 3.8. Getting approval: | - | 20. All dwg (mecha/elec/air layout)
|  | 3.9. Review schedule | - | 21. New revise schedule
|  | 3.10. Review planning in case asking out side maker | - | -
8 weeks
04 | ORDER | 4.1. Prepare, document then get approval (during issue dwg!?). Register to MEM book schedule to GM/FM/GD | 1 week | 22. Purchase approval document
|  | 4.2. Update order list to control plan (during issue dwg!?) | - | 23. Internal purchase control list
|  | 4.3. Mtg with (GIP/MEM/MTP/User..) to fix schedule; then Issue PRS to MEM; Assembly request to MTP | - | 24. Mtg minute.
|  | 4.4. Follow P/O; ETD; ETA of each part | 5 weeks | -
|  | 4.5. Review schedule | 1 day | 25. New revise schedule
6 weeks
05 | ASSEMBLY AND DEBUG | 5.1. Check ETA part follow Order list; MEM transfer to MTP then assemble | 2.5 weeks | 26. Part transferring check list
|  | 5.2. Confirm actual machine with requirement specification (DB machine) | 1.5 weeks | -
|  | 5.3. Meeting with related dep't (User/MTP/ISH/PQA/PE/PDC…) | - | 27. Mtg minute.
|  | 5.4. Summarize official testing data | 2 days | 28. Testing data sheet
|  | 5.5. Making manual | - | 29. Manual
|  | 5.6. Training MTP/PM | 1 day | 30. Training record
|  | 5.7. Spare part list up | - | 31. Spare part list
|  | 5.8. Internal confirmation | 1 day | 32. Schedule
5 weeks
06 | APPLY | 6.1. Install machine to workshop | 1 day | -
|  | 6.2. Training OP | 1 day | 33. Training record
|  | 6.3. Safety check by ISH and USER (confirm result of 1st checking) | 1 day | 34. Safety check sheet
|  | 6.4. TVP | 1 week | 35. TVP result
|  | 6.5. Machine shipping preparation | - | 36. Shipping approval document
|  | 6.6. Shipping approval (User/ISH/MTP) | 1 day | 37. Shipping approval sheet
|  | 6.7. Throw away investigation product parts | - | Follow PDC rule
2 weeks
07 | FOLLOW UP | 7.1. Follow machine performance | - | 38. Kaizen report/MC control sheet
|  | 7.2. Improve activity | - | 39. Problem control sheet
|  | 7.3. Feed back | - | 40. Changing point control
| 7 steps | 47 Jobs | 30 weeks | 40 kinds of document